## WBS
Work Breakdown Structure - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Level 1 = phase / workstream, Level 2 = work package (scheduled in 07_Project_Timeline and 08_Gantt_Chart), Level 3 = sub-task. Level 1 start, end and effort are formulas that roll up their work packages. Blue = input estimate (simulated, total across contributing roles).
WBS ID | Level | Element | Description / Deliverable | Responsible Role | Sprint | Planned Start | Planned End | Effort (person-days) | Linked Stories
1 | 1 | Project Initiation & Management | Governance, planning and control of the whole project. |  | S1-S5 | 2026-01-05 | 2026-03-13 | 23
1.1 | 2 | Kickoff, Project Charter & stakeholder register | Approved Project Charter; Stakeholder Register v1 | Project Manager | S1 | 2026-01-05 | 2026-01-07 | 4
1.1.1 | 3 | Draft charter and business case |  | Project Manager
1.1.2 | 3 | Identify stakeholders and draft register |  | Project Manager
1.1.3 | 3 | Charter review and approval (M1) |  | Project Manager
1.2 | 2 | Project planning (scope, WBS, schedule, risks, RACI, sprint plan) | Scope, WBS, timeline, Risk Register, RACI, Sprint Plan baseline | Project Manager | S1 | 2026-01-08 | 2026-01-14 | 6
1.2.1 | 3 | Scope statement and MoSCoW prioritisation |  | Project Manager
1.2.2 | 3 | WBS and milestone schedule |  | Project Manager
1.2.3 | 3 | Risk register baseline |  | Project Manager
1.2.4 | 3 | RACI and communication cadence |  | Project Manager
1.2.5 | 3 | Sprint plan and Definition of Done |  | Project Manager
1.3 | 2 | Monitoring & controlling (ceremonies, risk reviews, status reporting, change control) | Sprint reviews, status report, decision and change logs | Project Manager | S1-S5 | 2026-01-08 | 2026-03-13 | 13
1.3.1 | 3 | Sprint ceremonies (planning, review, retrospective) |  | Project Manager
1.3.2 | 3 | Weekly risk, issue and dependency review |  | Project Manager
1.3.3 | 3 | Status reporting and steering updates |  | Project Manager
1.3.4 | 3 | Change-control log |  | Project Manager
2 | 1 | Requirements | Understand the business need and baseline what must be built. |  | S1 | 2026-01-08 | 2026-01-16 | 12
2.1 | 2 | Requirements elicitation (interviews, ticket-category analysis) | Interview notes; ticket-category analysis | Product Manager | S1 | 2026-01-08 | 2026-01-13 | 6
2.1.1 | 3 | Stakeholder interviews (Support, Content, Security) |  | Product Manager
2.1.2 | 3 | Ticket-category analysis |  | Product Manager
2.1.3 | 3 | Current-process mapping |  | Product Manager
2.2 | 2 | Requirements documentation & baseline | Requirements v1.0 baseline; backlog estimated | Product Manager | S1 | 2026-01-12 | 2026-01-16 | 6
2.2.1 | 3 | Business and functional requirements |  | Product Manager
2.2.2 | 3 | Non-functional, security and AI requirements |  | Product Manager
2.2.3 | 3 | Requirements review and baseline (M2) |  | Product Manager
2.2.4 | 3 | Backlog creation and estimation |  | Product Manager
3 | 1 | UX / UI Design | User flows, wireframes, prototype and design handoff. |  | S1-S2 | 2026-01-08 | 2026-01-23 | 15
3.1 | 2 | UX research & user flows | User flows (chat, escalation, admin) | UI/UX Designer | S1 | 2026-01-08 | 2026-01-13 | 4
3.1.1 | 3 | Persona and journey review |  | UI/UX Designer
3.1.2 | 3 | User flows (chat, escalation, admin) |  | UI/UX Designer
3.2 | 2 | Wireframes & clickable prototype | Clickable prototype for all MVP screens | UI/UX Designer | S1 | 2026-01-12 | 2026-01-16 | 7 | US-03
3.2.1 | 3 | Low-fidelity wireframes |  | UI/UX Designer
3.2.2 | 3 | Clickable prototype |  | UI/UX Designer
3.2.3 | 3 | Product Owner prototype approval |  | UI/UX Designer
3.3 | 2 | Usability check with support agents & design handoff | Usability findings; design handoff package | UI/UX Designer | S2 | 2026-01-19 | 2026-01-23 | 4
3.3.1 | 3 | Usability sessions with 5 agents |  | UI/UX Designer
3.3.2 | 3 | Design refinements |  | UI/UX Designer
3.3.3 | 3 | Developer handoff |  | UI/UX Designer
4 | 1 | Backend | APIs, authentication, conversation and escalation services, security. |  | S1-S5 | 2026-01-12 | 2026-03-05 | 50
4.1 | 2 | Staff authentication & role-based access | Staff login; RBAC permission model | Backend Developer | S1 | 2026-01-12 | 2026-01-16 | 6 | US-04, US-05
4.1.1 | 3 | Staff login and session management |  | Backend Developer
4.1.2 | 3 | Role model and permission checks |  | Backend Developer
4.1.3 | 3 | Account lockout and password hashing |  | Backend Developer
4.2 | 2 | KB management APIs (CRUD, publish, bulk import) | KB APIs; import validation | Backend Developer | S2 | 2026-01-19 | 2026-01-28 | 8 | US-09, US-10
4.2.1 | 3 | Article CRUD and publish API |  | Backend Developer
4.2.2 | 3 | Bulk import API and validation |  | Backend Developer
4.2.3 | 3 | Trigger ingestion on publish |  | Backend Developer
4.3 | 2 | Customer sign-in (email one-time code) | Customer OTP sign-in | Backend Developer | S3 | 2026-02-02 | 2026-02-06 | 4 | US-06
4.3.1 | 3 | OTP generation and verification |  | Backend Developer
4.3.2 | 3 | Customer session and attempt limits |  | Backend Developer
4.4 | 2 | Chat, conversation-history & escalation-request APIs | Chat, history and escalation-request APIs | Backend Developer | S3 | 2026-02-02 | 2026-02-11 | 8 | US-18, US-19
4.4.1 | 3 | Chat message API |  | Backend Developer
4.4.2 | 3 | Conversation storage and history API |  | Backend Developer
4.4.3 | 3 | Escalation-request API |  | Backend Developer
4.5 | 2 | Escalation queue, agent reply & notification APIs | Queue, claim, reply, resolve and notification APIs | Backend Developer | S4 | 2026-02-16 | 2026-02-24 | 8 | US-20, US-21, US-22
4.5.1 | 3 | Escalation queue and claim API |  | Backend Developer
4.5.2 | 3 | Agent reply and resolve API |  | Backend Developer
4.5.3 | 3 | Customer notification (in-chat and email) |  | Backend Developer
4.6 | 2 | Event tracking & analytics APIs | Event schema and aggregation queries | Backend Developer | S4 | 2026-02-16 | 2026-02-19 | 4 | US-23
4.6.1 | 3 | Event schema and logging |  | Backend Developer
4.6.2 | 3 | Aggregation queries for dashboard |  | Backend Developer
4.7 | 2 | Security hardening | Rate limiting, validation, secrets, dependency scans | Backend Developer | S4 | 2026-02-16 | 2026-02-25 | 6 | US-07
4.7.1 | 3 | Rate limiting and input validation |  | Backend Developer
4.7.2 | 3 | Secrets management and dependency scans |  | Backend Developer
4.7.3 | 3 | Prompt-injection test cases |  | Backend Developer
4.8 | 2 | Data retention, deletion & audit logging | Retention job; customer data deletion; audit log | Backend Developer | S5 | 2026-03-02 | 2026-03-05 | 6 | US-26, US-08
4.8.1 | 3 | Retention job |  | Backend Developer
4.8.2 | 3 | Customer data deletion |  | Backend Developer
4.8.3 | 3 | Audit logging |  | Backend Developer
5 | 1 | AI Integration | Retrieval-augmented generation, guardrails, PII redaction and tuning. |  | S1-S3 | 2026-01-08 | 2026-02-11 | 36
5.1 | 2 | LLM & embedding evaluation spike | Spike report; provider recommendation + fallback option | AI/ML Engineer | S1 | 2026-01-08 | 2026-01-16 | 7 | US-11
5.1.1 | 3 | Define evaluation criteria and sample questions |  | AI/ML Engineer
5.1.2 | 3 | Benchmark LLM and embedding options |  | AI/ML Engineer
5.1.3 | 3 | Recommendation and fallback option memo |  | AI/ML Engineer
5.2 | 2 | KB ingestion pipeline (chunk, embed, index) | Ingestion pipeline; re-index job | AI/ML Engineer | S2 | 2026-01-19 | 2026-01-27 | 9 | US-12
5.2.1 | 3 | Chunking strategy |  | AI/ML Engineer
5.2.2 | 3 | Embedding and indexing job |  | AI/ML Engineer
5.2.3 | 3 | Re-index and unpublish handling |  | AI/ML Engineer
5.3 | 2 | RAG answer service with citations, guardrails & fallback | RAG answer API; fallback and out-of-scope handling | AI/ML Engineer | S2 | 2026-01-22 | 2026-01-30 | 11 | US-13, US-14
5.3.1 | 3 | Retrieval and ranking |  | AI/ML Engineer
5.3.2 | 3 | Grounded answer prompt and citations |  | AI/ML Engineer
5.3.3 | 3 | Confidence threshold and fallback |  | AI/ML Engineer
5.3.4 | 3 | Out-of-scope handling |  | AI/ML Engineer
5.4 | 2 | PII redaction & answer-quality tuning | PII redaction layer; tuned prompts and thresholds | AI/ML Engineer | S3 | 2026-02-02 | 2026-02-11 | 9 | US-25
5.4.1 | 3 | PII redaction layer |  | AI/ML Engineer
5.4.2 | 3 | Prompt and threshold tuning from evaluation results |  | AI/ML Engineer
5.4.3 | 3 | Token limits and cost controls |  | AI/ML Engineer
6 | 1 | Database & Data | Data model, vector store and knowledge-base content readiness. |  | S1-S2 | 2026-01-12 | 2026-01-30 | 16
6.1 | 2 | Data model & schema | Schema v1 and migrations; backup configuration | Backend Developer | S1 | 2026-01-12 | 2026-01-16 | 4 | US-02
6.1.1 | 3 | Entity model and relationships |  | Backend Developer
6.1.2 | 3 | Migrations and backup configuration |  | Backend Developer
6.2 | 2 | Vector store setup & seed KB load | Vector index ready; cleaned KB loaded | AI/ML Engineer | S2 | 2026-01-19 | 2026-01-23 | 4 | US-12
6.2.1 | 3 | Vector extension setup |  | AI/ML Engineer
6.2.2 | 3 | Load cleaned KB (approx. 280 articles) |  | AI/ML Engineer
6.3 | 2 | KB content audit & cleanup (with Support SMEs) | Audited KB: duplicates removed, outdated articles fixed | Product Manager | S1-S2 | 2026-01-12 | 2026-01-30 | 8
6.3.1 | 3 | Export legacy help-center articles (320) |  | Product Manager
6.3.2 | 3 | Remove duplicates and flag outdated articles |  | Product Manager
6.3.3 | 3 | Rewrite priority articles with Support SMEs |  | Product Manager
7 | 1 | Frontend | Customer chat, admin, agent console and manager dashboard. |  | S2-S4 | 2026-01-19 | 2026-02-27 | 41
7.1 | 2 | Frontend scaffold & Admin KB UI | App scaffold; admin KB list, editor and import screens | Frontend Developer | S2 | 2026-01-19 | 2026-01-30 | 11 | US-09, US-10
7.1.1 | 3 | App scaffold and design system |  | Frontend Developer
7.1.2 | 3 | Staff login screens |  | Frontend Developer
7.1.3 | 3 | Admin KB list, editor and import screens |  | Frontend Developer
7.2 | 2 | Customer chat UI (chat, feedback, history, 'Talk to a person') | Customer chat experience | Frontend Developer | S3 | 2026-02-02 | 2026-02-13 | 13 | US-16, US-17, US-18, US-19
7.2.1 | 3 | Customer OTP sign-in screens |  | Frontend Developer
7.2.2 | 3 | Chat window with sources |  | Frontend Developer
7.2.3 | 3 | Feedback control |  | Frontend Developer
7.2.4 | 3 | History view |  | Frontend Developer
7.2.5 | 3 | 'Talk to a person' flow |  | Frontend Developer
7.3 | 2 | Agent console UI | Escalation queue and agent console | Frontend Developer | S4 | 2026-02-16 | 2026-02-25 | 11 | US-20, US-21
7.3.1 | 3 | Escalation queue view |  | Frontend Developer
7.3.2 | 3 | Transcript and reply panel |  | Frontend Developer
7.3.3 | 3 | Resolve and release actions |  | Frontend Developer
7.4 | 2 | Manager dashboard UI | Analytics dashboard | Frontend Developer | S4 | 2026-02-20 | 2026-02-27 | 6 | US-24
7.4.1 | 3 | KPI tiles and trend charts |  | Frontend Developer
7.4.2 | 3 | Fallback-topics table |  | Frontend Developer
8 | 1 | Integration | Connecting components and third-party services end to end. |  | S3-S4 | 2026-02-02 | 2026-02-27 | 13
8.1 | 2 | Email provider integration (OTP & notifications) | Email integration; SPF/DKIM verified | Backend Developer | S3 | 2026-02-02 | 2026-02-04 | 2 | US-06
8.1.1 | 3 | Provider account and domain verification (SPF/DKIM) |  | Backend Developer
8.1.2 | 3 | OTP and notification templates |  | Backend Developer
8.2 | 2 | End-to-end chat integration (UI - API - RAG - DB) | Integrated chat flow in staging; demo | Backend Developer | S3 | 2026-02-09 | 2026-02-13 | 6 | US-16, US-19
8.2.1 | 3 | UI-API contract tests |  | Backend Developer
8.2.2 | 3 | RAG-chat API integration |  | Backend Developer
8.2.3 | 3 | Error and timeout handling |  | Backend Developer
8.3 | 2 | Full escalation-flow integration (chat - queue - agent - customer) | Feature-complete build in staging | Backend Developer | S4 | 2026-02-24 | 2026-02-27 | 5 | US-22
8.3.1 | 3 | Chat-escalation-agent-customer test script |  | Backend Developer
8.3.2 | 3 | Integration defect triage |  | Backend Developer
9 | 1 | Testing & Quality | Test strategy, AI quality evaluation, security, performance and UAT. |  | S2-S5 | 2026-01-19 | 2026-03-06 | 35
9.1 | 2 | Test strategy & golden Q&A set | Test strategy; golden set (100+ questions); evaluation script | QA Engineer | S2 | 2026-01-19 | 2026-01-30 | 6 | US-15
9.1.1 | 3 | Test strategy and test environments |  | QA Engineer
9.1.2 | 3 | Golden Q&A set (100+) |  | QA Engineer
9.1.3 | 3 | Evaluation script |  | QA Engineer
9.2 | 2 | Sprint QA & AI quality evaluation runs (#1 baseline, #2 post-tuning) | Evaluation reports #1 and #2; regression results | QA Engineer | S3-S4 | 2026-02-09 | 2026-02-27 | 10
9.2.1 | 3 | Sprint functional and regression testing |  | QA Engineer
9.2.2 | 3 | AI evaluation run #1 (baseline) |  | QA Engineer
9.2.3 | 3 | AI evaluation run #2 (post-tuning) |  | QA Engineer
9.3 | 2 | Security testing | Access-control, injection and prompt-injection test results | QA Engineer | S4 | 2026-02-23 | 2026-02-27 | 4 | US-07
9.3.1 | 3 | Access-control tests |  | QA Engineer
9.3.2 | 3 | Prompt-injection and input tests |  | QA Engineer
9.3.3 | 3 | Vulnerability scan review |  | QA Engineer
9.4 | 2 | Performance & load testing | Load test report (50 concurrent sessions) | QA Engineer | S5 | 2026-03-02 | 2026-03-04 | 3 | US-27
9.4.1 | 3 | Load scenario and tooling |  | QA Engineer
9.4.2 | 3 | 50-session test and report |  | QA Engineer
9.5 | 2 | UAT preparation | UAT test cases; participants and environment ready | QA Engineer | S4 | 2026-02-23 | 2026-02-27 | 3
9.5.1 | 3 | UAT plan and test cases |  | QA Engineer
9.5.2 | 3 | UAT participants and environment |  | QA Engineer
9.6 | 2 | UAT execution & defect fixing | UAT results; defect fixes; written UAT sign-off | QA Engineer | S5 | 2026-03-02 | 2026-03-06 | 9 | US-28
9.6.1 | 3 | UAT execution |  | QA Engineer
9.6.2 | 3 | Defect triage and fixes |  | QA Engineer
9.6.3 | 3 | Regression and sign-off (M6) |  | QA Engineer
10 | 1 | Deployment | Environments, CI/CD, monitoring, Go/No-Go and pilot release. |  | S1-S5 | 2026-01-08 | 2026-03-13 | 17
10.1 | 2 | Environments & CI/CD pipeline | Dev/staging/prod environments; CI/CD pipeline | DevOps Engineer | S1 | 2026-01-08 | 2026-01-16 | 6 | US-01
10.1.1 | 3 | Dev, staging and production environments |  | DevOps Engineer
10.1.2 | 3 | CI/CD pipeline |  | DevOps Engineer
10.1.3 | 3 | Secrets and TLS |  | DevOps Engineer
10.2 | 2 | Monitoring, alerts & staging release rehearsal | Dashboards and alerts; rehearsed rollback | DevOps Engineer | S5 | 2026-03-02 | 2026-03-06 | 5 | US-29
10.2.1 | 3 | Monitoring and alerts (errors, latency, LLM spend) |  | DevOps Engineer
10.2.2 | 3 | Staging release and rollback rehearsal |  | DevOps Engineer
10.3 | 2 | Go / No-Go review | Signed Go/No-Go checklist | Project Manager | S5 | 2026-03-09 | 2026-03-09 | 1
10.3.1 | 3 | Go/No-Go checklist review (M7) |  | Project Manager
10.4 | 2 | Production pilot release | Production deployment; smoke-test results | DevOps Engineer | S5 | 2026-03-10 | 2026-03-11 | 2 | US-29
10.4.1 | 3 | Production deployment (M8) |  | DevOps Engineer
10.4.2 | 3 | Smoke tests |  | DevOps Engineer
10.5 | 2 | Hypercare & monitoring | Daily health check; hot-fix log | DevOps Engineer | S5 | 2026-03-11 | 2026-03-13 | 3
10.5.1 | 3 | Daily health checks |  | DevOps Engineer
10.5.2 | 3 | Hot-fix handling |  | DevOps Engineer
11 | 1 | Documentation & Training | User guides, technical documentation and training. |  | S4-S5 | 2026-02-23 | 2026-03-10 | 12
11.1 | 2 | User guides & training materials | Admin guide; agent guide; 'what the AI can/cannot answer' sheet | Product Manager | S4-S5 | 2026-02-23 | 2026-03-06 | 6 | US-30
11.1.1 | 3 | Admin guide |  | Product Manager
11.1.2 | 3 | Agent guide |  | Product Manager
11.1.3 | 3 | 'What the AI can and cannot answer' reference |  | Product Manager
11.2 | 2 | Technical documentation & runbook | Architecture and API docs; operations runbook | Backend Developer | S5 | 2026-03-02 | 2026-03-06 | 4
11.2.1 | 3 | Architecture and API documentation |  | Backend Developer
11.2.2 | 3 | Runbook (deploy, rollback, incidents) |  | Backend Developer
11.3 | 2 | Support team training session | 60-minute training delivered; practice tasks completed | Product Manager | S5 | 2026-03-09 | 2026-03-10 | 2 | US-30
11.3.1 | 3 | Training session (60 minutes) |  | Product Manager
11.3.2 | 3 | Practice tasks and Q&A |  | Product Manager
12 | 1 | Closure | Acceptance, handover, closure report and lessons learned. |  | S5 | 2026-03-11 | 2026-03-13 | 5
12.1 | 2 | Final acceptance & handover to Support Operations | Sponsor acceptance; handover pack; post-MVP backlog transferred | Project Manager | S5 | 2026-03-11 | 2026-03-12 | 2
12.1.1 | 3 | Final acceptance and Sponsor sign-off |  | Project Manager
12.1.2 | 3 | Handover to Support Operations; post-MVP backlog transfer |  | Project Manager
12.2 | 2 | Project Closure Report & lessons learned | Closure Report; Lessons Learned | Project Manager | S5 | 2026-03-12 | 2026-03-13 | 3
12.2.1 | 3 | Project Closure Report |  | Project Manager
12.2.2 | 3 | Lessons-learned retrospective (M9) |  | Project Manager
|  | Total planned effort (person-days) |  |  |  | 2026-01-05 | 2026-03-13 | 275
Formulas:
Planned Start = MIN([Planned Start, row below]:G21)
Planned Start = MIN(G6:[Planned Start, row above])
Planned End = MAX([Planned End, row below]:H21)
Planned End = MAX(H6:[Planned End, row above])

## Capacity Check
Capacity vs Planned Effort
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Checks that the WBS effort fits the team plan and leaves a visible buffer for estimation error (Risk R09). FTE values are simulated planning assumptions.
Role | FTE (planning assumption) | Project weeks | Person-weeks | Person-days
Project Manager | 1 | 10 | 10 | 50
Product Manager | 0.5 | 10 | 5 | 25
AI/ML Engineer | 1 | 10 | 10 | 50
Backend Developer | 1 | 10 | 10 | 50
Frontend Developer | 1 | 10 | 10 | 50
UI/UX Designer | 0.4 | 10 | 4 | 20
QA Engineer | 0.8 | 10 | 8 | 40
DevOps Engineer | 0.4 | 10 | 4 | 20
Team capacity | 6.1 |  | 61 | 305
Planned effort from WBS (person-days) | 275
Team capacity (person-days) | 305
Unallocated buffer (person-days) | 30
Buffer as % of capacity | 9.836%
Planned effort per work package is the total across all contributing roles. It is an estimate made at planning time, not a measured actual. The buffer is intentionally kept at roughly 10% of capacity.