## Gantt
Gantt Chart - AI Customer Support Platform (10 weeks, 5 two-week sprints)
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Project start (Monday) |  |  | 2026-01-05 | Bars are driven by the Start / End columns and by conditional formatting; edit a date and the bar moves. Day columns skip weekends (no public holidays assumed).
Sprint / week bands | [7 empty] | Sprint 1: Foundation | [9 empty] | Sprint 2: KB & AI core | [9 empty] | Sprint 3: Customer chat | [9 empty] | Sprint 4: Handover | [9 empty] | Sprint 5: Release
[8 empty] | W1 5 Jan |  |  |  |  | W2 12 Jan |  |  |  |  | W3 19 Jan |  |  |  |  | W4 26 Jan |  |  |  |  | W5 2 Feb |  |  |  |  | W6 9 Feb |  |  |  |  | W7 16 Feb |  |  |  |  | W8 23 Feb |  |  |  |  | W9 2 Mar |  |  |  |  | W10 9 Mar
ID | Work package / milestone | Workstream | Responsible role | Start | End | Days | Sprint | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13
1 | Project Initiation & Management
1.1 | Kickoff, Project Charter & stakeholder register [M1] | Project Management | Project Manager | 2026-01-05 | 2026-01-07 | 3 | S1
1.2 | Project planning (scope, WBS, schedule, risks, RACI, sprint plan) | Project Management | Project Manager | 2026-01-08 | 2026-01-14 | 5 | S1
1.3 | Monitoring & controlling (ceremonies, risk reviews, status reporting, change control) | Project Management | Project Manager | 2026-01-08 | 2026-03-13 | 47 | S1-S5
2 | Requirements
2.1 | Requirements elicitation (interviews, ticket-category analysis) | Requirements & UX | Product Manager | 2026-01-08 | 2026-01-13 | 4 | S1
2.2 | Requirements documentation & baseline [M2] | Requirements & UX | Product Manager | 2026-01-12 | 2026-01-16 | 5 | S1
3 | UX / UI Design
3.1 | UX research & user flows | Requirements & UX | UI/UX Designer | 2026-01-08 | 2026-01-13 | 4 | S1
3.2 | Wireframes & clickable prototype | Requirements & UX | UI/UX Designer | 2026-01-12 | 2026-01-16 | 5 | S1
3.3 | Usability check with support agents & design handoff | Requirements & UX | UI/UX Designer | 2026-01-19 | 2026-01-23 | 5 | S2
4 | Backend
4.1 | Staff authentication & role-based access | Backend, Data & Integration | Backend Developer | 2026-01-12 | 2026-01-16 | 5 | S1
4.2 | KB management APIs (CRUD, publish, bulk import) | Backend, Data & Integration | Backend Developer | 2026-01-19 | 2026-01-28 | 8 | S2
4.3 | Customer sign-in (email one-time code) | Backend, Data & Integration | Backend Developer | 2026-02-02 | 2026-02-06 | 5 | S3
4.4 | Chat, conversation-history & escalation-request APIs | Backend, Data & Integration | Backend Developer | 2026-02-02 | 2026-02-11 | 8 | S3
4.5 | Escalation queue, agent reply & notification APIs | Backend, Data & Integration | Backend Developer | 2026-02-16 | 2026-02-24 | 7 | S4
4.6 | Event tracking & analytics APIs | Backend, Data & Integration | Backend Developer | 2026-02-16 | 2026-02-19 | 4 | S4
4.7 | Security hardening | Backend, Data & Integration | Backend Developer | 2026-02-16 | 2026-02-25 | 8 | S4
4.8 | Data retention, deletion & audit logging | Backend, Data & Integration | Backend Developer | 2026-03-02 | 2026-03-05 | 4 | S5
5 | AI Integration
5.1 | LLM & embedding evaluation spike | AI | AI/ML Engineer | 2026-01-08 | 2026-01-16 | 7 | S1
5.2 | KB ingestion pipeline (chunk, embed, index) | AI | AI/ML Engineer | 2026-01-19 | 2026-01-27 | 7 | S2
5.3 | RAG answer service with citations, guardrails & fallback [M3] | AI | AI/ML Engineer | 2026-01-22 | 2026-01-30 | 7 | S2
5.4 | PII redaction & answer-quality tuning | AI | AI/ML Engineer | 2026-02-02 | 2026-02-11 | 8 | S3
6 | Database & Data
6.1 | Data model & schema | Backend, Data & Integration | Backend Developer | 2026-01-12 | 2026-01-16 | 5 | S1
6.2 | Vector store setup & seed KB load | Backend, Data & Integration | AI/ML Engineer | 2026-01-19 | 2026-01-23 | 5 | S2
6.3 | KB content audit & cleanup (with Support SMEs) | Backend, Data & Integration | Product Manager | 2026-01-12 | 2026-01-30 | 15 | S1-S2
7 | Frontend
7.1 | Frontend scaffold & Admin KB UI | Frontend | Frontend Developer | 2026-01-19 | 2026-01-30 | 10 | S2
7.2 | Customer chat UI (chat, feedback, history, 'Talk to a person') | Frontend | Frontend Developer | 2026-02-02 | 2026-02-13 | 10 | S3
7.3 | Agent console UI | Frontend | Frontend Developer | 2026-02-16 | 2026-02-25 | 8 | S4
7.4 | Manager dashboard UI | Frontend | Frontend Developer | 2026-02-20 | 2026-02-27 | 6 | S4
8 | Integration
8.1 | Email provider integration (OTP & notifications) | Backend, Data & Integration | Backend Developer | 2026-02-02 | 2026-02-04 | 3 | S3
8.2 | End-to-end chat integration (UI - API - RAG - DB) [M4] | Backend, Data & Integration | Backend Developer | 2026-02-09 | 2026-02-13 | 5 | S3
8.3 | Full escalation-flow integration (chat - queue - agent - customer) [M5] | Backend, Data & Integration | Backend Developer | 2026-02-24 | 2026-02-27 | 4 | S4
9 | Testing & Quality
9.1 | Test strategy & golden Q&A set | Testing & QA | QA Engineer | 2026-01-19 | 2026-01-30 | 10 | S2
9.2 | Sprint QA & AI quality evaluation runs (#1 baseline, #2 post-tuning) | Testing & QA | QA Engineer | 2026-02-09 | 2026-02-27 | 15 | S3-S4
9.3 | Security testing | Testing & QA | QA Engineer | 2026-02-23 | 2026-02-27 | 5 | S4
9.4 | Performance & load testing | Testing & QA | QA Engineer | 2026-03-02 | 2026-03-04 | 3 | S5
9.5 | UAT preparation | Testing & QA | QA Engineer | 2026-02-23 | 2026-02-27 | 5 | S4
9.6 | UAT execution & defect fixing [M6] | Testing & QA | QA Engineer | 2026-03-02 | 2026-03-06 | 5 | S5
10 | Deployment
10.1 | Environments & CI/CD pipeline | Release & Documentation | DevOps Engineer | 2026-01-08 | 2026-01-16 | 7 | S1
10.2 | Monitoring, alerts & staging release rehearsal | Release & Documentation | DevOps Engineer | 2026-03-02 | 2026-03-06 | 5 | S5
10.3 | Go / No-Go review [M7] | Release & Documentation | Project Manager | 2026-03-09 | 2026-03-09 | 1 | S5
10.4 | Production pilot release [M8] | Release & Documentation | DevOps Engineer | 2026-03-10 | 2026-03-11 | 2 | S5
10.5 | Hypercare & monitoring | Release & Documentation | DevOps Engineer | 2026-03-11 | 2026-03-13 | 3 | S5
11 | Documentation & Training
11.1 | User guides & training materials | Release & Documentation | Product Manager | 2026-02-23 | 2026-03-06 | 10 | S4-S5
11.2 | Technical documentation & runbook | Release & Documentation | Backend Developer | 2026-03-02 | 2026-03-06 | 5 | S5
11.3 | Support team training session | Release & Documentation | Product Manager | 2026-03-09 | 2026-03-10 | 2 | S5
12 | Closure
12.1 | Final acceptance & handover to Support Operations | Project Management | Project Manager | 2026-03-11 | 2026-03-12 | 2 | S5
12.2 | Project Closure Report & lessons learned [M9] | Project Management | Project Manager | 2026-03-12 | 2026-03-13 | 2 | S5
MS | Milestones (diamond marks the date)
M1 | Project Charter approved | Milestone |  | 2026-01-07 | 2026-01-07 |  | S1 |  |  | ◆
M2 | Requirements & UX baseline approved | Milestone |  | 2026-01-16 | 2026-01-16 |  | S1 | [9 empty] | ◆
M3 | Sprint 2 review: KB ingestion + RAG answers demo | Milestone |  | 2026-01-30 | 2026-01-30 |  | S2 | [19 empty] | ◆
M4 | Sprint 3 review: customer chat + escalation request demo | Milestone |  | 2026-02-13 | 2026-02-13 |  | S3 | [29 empty] | ◆
M5 | Feature complete / code freeze | Milestone |  | 2026-02-27 | 2026-02-27 |  | S4 | [39 empty] | ◆
M6 | UAT sign-off | Milestone |  | 2026-03-06 | 2026-03-06 |  | S5 | [44 empty] | ◆
M7 | Go / No-Go decision | Milestone |  | 2026-03-09 | 2026-03-09 |  | S5 | [45 empty] | ◆
M8 | Pilot release to production | Milestone |  | 2026-03-11 | 2026-03-11 |  | S5 | [47 empty] | ◆
M9 | Project closure | Milestone |  | 2026-03-13 | 2026-03-13 |  | S5 | [49 empty] | ◆
Legend (bar colour = workstream)
Project Management
Requirements & UX
Backend, Data & Integration
AI
Frontend
Testing & QA
Release & Documentation
◆ | Milestone (M1-M9; see 07_Project_Timeline)