## Stakeholder Register
Stakeholder Register - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
All names are fictional. Interest and influence are scored 1 (low) to 5 (high) by the PM at project start; the strategy column is a formula: Influence >= 4 and Interest >= 4 = Manage closely; Influence >= 4 = Keep satisfied; Interest >= 4 = Keep informed; otherwise Monitor.
ID | Stakeholder | Type | Role in project | Decision maker? | Interest (1-5) | Influence (1-5) | Strategy (Power / Interest) | Expectations | Engagement approach | Communication needs
S-01 | Marcus Hale - VP Customer Experience | Internal | Executive Sponsor; funds the project and decides Go/No-Go | Yes | 4 | 5 | Manage closely | Fewer routine tickets, faster responses, no brand-damaging AI errors, delivery within budget. | Steering review at every sprint review; decisions brought with a recommendation and options; early warning on red items. | Fortnightly one-page summary; ad-hoc decision memos; Go/No-Go meeting.
S-02 | Elena Rossi - Product Manager (Product Owner) | Internal | Owns backlog, priorities and acceptance of stories | Yes | 5 | 4 | Manage closely | A prioritised, value-driven backlog; clear trade-offs; predictable sprint outcomes. | Daily contact; joint backlog refinement; sprint planning and review; agrees any scope trade-off before it reaches the Sponsor. | Daily stand-up; refinement; sprint review; decision log.
S-03 | Sofia Lindqvist - Support Manager | Internal | Business owner of support operations; UAT lead and approver | Yes | 5 | 4 | Manage closely | Agents relieved of routine work, smooth escalations, trustworthy answers, visibility through analytics. | Workshops in discovery; sprint review demos; weekly check on AI conversation samples during pilot; owns UAT sign-off. | Sprint review; weekly 30-minute sync; UAT briefings.
S-04 | Raj Patel - CTO / Head of Engineering | Internal | Approves architecture, security stance and engineering capacity | Yes | 3 | 5 | Keep satisfied | Maintainable, secure design that fits company standards; no uncontrolled technical debt. | Architecture review at end of Sprint 1; short technical risk update each sprint; escalation path for resourcing. | Sprint review (optional); architecture review; monthly risk summary.
S-05 | Hannah Weber - Security & Privacy Officer | Internal | Reviews privacy and security controls; go-live gatekeeper | Yes | 3 | 4 | Keep satisfied | Documented controls, provider terms confirmed, no Critical/High vulnerabilities, auditable data handling. | Early review of data flow and provider terms (Sprint 1-2); test results review in Sprint 4-5; attends Go/No-Go. | Review meetings at milestones M2, M5, M7; written approvals.
S-06 | Daniel Moreau - Customer Success Lead | Internal | Consumer of analytics; represents merchant voice; raised CR-001 | No | 4 | 3 | Keep informed | Insight into merchant questions and content gaps; ability to request improvements. | Sprint review invitations; early look at dashboard; structured intake of change requests through Product Owner. | Sprint review; dashboard preview in Sprint 4.
S-07 | Aiden Park - Knowledge & Content Lead (KB Admin) | Internal | Admin end user; owns KB content quality | No | 5 | 3 | Keep informed | Simple editing and import tools; clear ownership of content; feedback on gaps. | Co-design admin screens; leads content audit with Product Manager; trained in Sprint 5. | Weekly content sync during Sprints 1-3; training session.
S-08 | Jamal Brooks and the 14 support agents | Internal | Agent end users; usability testers and UAT participants | No | 5 | 3 | Keep informed | Fewer repetitive tickets; full context on escalations; a tool that does not slow them down. | Usability sessions in Sprint 2; demo in Sprint 4; named UAT group; training in Sprint 5; feedback channel. | Usability sessions; UAT briefing; training; hypercare channel.
S-09 | Finance Partner | Internal | Oversees non-labour budget | No | 2 | 3 | Monitor | Spend within the 5,500 USD plan; early warning on overrun. | Monthly spend update; alert if LLM spend passes 70%. | Monthly budget line in status report.
S-10 | Legal & Compliance Counsel | Internal | Reviews provider terms and AI disclosure wording | Yes | 2 | 4 | Keep satisfied | Contract terms that protect customer data; clear AI disclosure to customers. | Provider terms review request in Sprint 1; wording review for AI label in Sprint 3. | Written review requests with deadlines; milestone notice.
S-11 | Project delivery team (AI/ML, Backend, Frontend, UX, QA, DevOps) | Internal | Designs, builds and tests the platform | No | 5 | 4 | Manage closely | Clear priorities, stable sprint scope, fast decisions, protected focus time. | Sprint ceremonies; PM removes blockers; open retrospectives. | Daily stand-up; planning, review, retrospective; shared board.
S-12 | Merchant customers (pilot cohort) | External | End users of the chat assistant | No | 3 | 2 | Monitor | Fast, correct answers; easy route to a human; privacy respected. | Represented by Support and Customer Success; AI disclosure and feedback buttons in product; pilot feedback review. | In-product notices; pilot feedback summary.
S-13 | LLM / embedding API provider | External | Third-party supplier of AI models | No | 2 | 3 | Monitor | Compliant use of the API; payment. | Single technical contact; track terms, quotas and model deprecation notices. | Vendor portal; account contact.
S-14 | Transactional email provider | External | Supplier of OTP and notification emails | No | 1 | 2 | Monitor | Verified sending domain; normal usage volumes. | Domain verification in Sprint 3; delivery monitoring. | Vendor portal.
S-15 | Data-protection regulators (indirect) | External | Set the rules the privacy controls must respect | No | 1 | 4 | Keep satisfied | Compliance with data-protection principles. | Engaged indirectly through the Security & Privacy Officer. | None directly.

## Power-Interest Grid
Power / Interest Grid
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Stakeholder IDs placed by the same rule as the register (static text generated from the register scores; refresh if scores change). Counts are live formulas.
| LOW INTEREST (1-3) | HIGH INTEREST (4-5)
HIGH INFLUENCE (4-5) | KEEP SATISFIED S-04 Raj Patel S-05 Hannah Weber S-10 Legal & Compliance Counsel S-15 Data-protection regulators (indirect) | MANAGE CLOSELY S-01 Marcus Hale S-02 Elena Rossi S-03 Sofia Lindqvist S-11 Project delivery team (AI/ML, Backend, Frontend, UX, QA, DevOps)
LOW INFLUENCE (1-3) | MONITOR S-09 Finance Partner S-12 Merchant customers (pilot cohort) S-13 LLM / embedding API provider S-14 Transactional email provider | KEEP INFORMED S-06 Daniel Moreau S-07 Aiden Park S-08 Jamal Brooks and the 14 support agents
Strategy | Stakeholders (count)
Manage closely | 4
Keep satisfied | 4
Keep informed | 3
Monitor | 4