## RACI
RACI Matrix - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
R = Responsible, A = Accountable, C = Consulted, I = Informed. 'A/R' means the same role is accountable and does the work. Rule: exactly one A per activity and at least one R (checked by formula). Executive Sponsor and Steering Committee approvals sit outside the delivery roles shown; where a sponsor sign-off is needed the Project Manager is accountable for obtaining it. The Backend Developer acts as technical lead.
Activity | Project Manager | Product Manager | AI/ML Engineer | Backend Developer | Frontend Developer | UI/UX Designer | QA Engineer | DevOps Engineer | A count | R count | Check
Project Charter and business case | A/R | C | C | C | I | I | I | I | 1 | 1 | OK
Scope baseline and change control | A | R | C | C | C | C | C | I | 1 | 1 | OK
Requirements elicitation and documentation | R | A/R | C | C | C | C | C | I | 1 | 2 | OK
Backlog creation, prioritisation and refinement | R | A/R | C | C | C | C | C | I | 1 | 2 | OK
Sprint planning and sprint goals | A | R | R | R | R | C | R | C | 1 | 5 | OK
Schedule, WBS and milestone tracking | A/R | C | I | I | I | I | I | I | 1 | 1 | OK
Risk, issue and dependency management | A/R | C | C | C | C | I | C | C | 1 | 1 | OK
Stakeholder communication and status reporting | A/R | C | I | I | I | I | I | I | 1 | 1 | OK
UX research, wireframes and prototype | I | C | I | I | C | A/R | I | I | 1 | 1 | OK
Solution architecture and technology choices | C | C | R | A/R | C | I | C | R | 1 | 3 | OK
LLM and embedding evaluation (spike) | C | C | A/R | C | I | I | C | C | 1 | 1 | OK
Database design and schema | I | I | C | A/R | C | I | I | C | 1 | 1 | OK
Authentication and role-based access | I | C | I | A/R | C | I | C | C | 1 | 1 | OK
KB ingestion pipeline and RAG service | I | C | A/R | C | I | I | C | C | 1 | 1 | OK
Guardrails, PII redaction and fallback logic | I | C | A/R | C | I | C | C | I | 1 | 1 | OK
Frontend development (chat, admin, agent, dashboard) | I | C | I | C | A/R | C | C | I | 1 | 1 | OK
API and integration (email, LLM, end-to-end flows) | I | I | R | A/R | R | I | C | C | 1 | 3 | OK
Test strategy, golden set and AI evaluation | I | C | R | C | C | I | A/R | I | 1 | 2 | OK
Security testing and vulnerability management | I | I | C | R | C | I | A | R | 1 | 2 | OK
Performance and load testing | I | I | C | C | I | I | A/R | R | 1 | 2 | OK
UAT planning and coordination | A | R | C | C | C | I | R | I | 1 | 2 | OK
Environments, CI/CD and monitoring | I | I | C | C | C | I | C | A/R | 1 | 1 | OK
Go/No-Go and production release | A | R | C | C | C | I | R | R | 1 | 3 | OK
Documentation and user training | C | A/R | C | R | C | C | R | C | 1 | 3 | OK
Project closure and lessons learned | A/R | R | C | C | C | C | C | C | 1 | 2 | OK
Activities passing check | 25 of 25

## Team Roles & PM Needs
Project Team: Responsibilities, Dependencies and PM Needs
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
The PM coordinates and removes blockers; the PM does not perform the technical work. FTE values are simulated planning assumptions.
Role | FTE (planning) | Person-weeks (10 wks) | Responsibilities | Dependencies | What the PM needs from this role
Project Manager | 1 | 10 | Plans and controls the project: scope baseline, schedule, risks, issues, dependencies, change control, stakeholder communication, status reporting; facilitates Scrum ceremonies and removes blockers. Does not design, code or test. | Product Manager for priorities; Sponsor for decisions and budget; team leads for estimates. | Honest estimates and early warning of slippage; updates on the board daily; named risk owners acting on mitigations.
Product Manager | 0.5 | 5 | Owns the product vision and backlog; sets priorities and accepts stories; leads requirements and content readiness; trains Support users. | Support Manager and KB Admin for domain knowledge; PM for planning support. | Timely prioritisation decisions (within 2 business days); acceptance of finished stories during the sprint; ownership of content quality.
AI/ML Engineer | 1 | 10 | Evaluates and integrates LLM and embedding models; builds ingestion, retrieval, answer generation, guardrails and PII redaction; tunes prompts and thresholds using evaluation results. | Backend (APIs, DB); QA (golden set); Security & Privacy Officer (provider terms); Product Manager (content). | Evaluation results each sprint with failure causes; clear flag when quality targets are at risk; cost and latency numbers.
Backend Developer | 1 | 10 | Builds APIs, authentication, RBAC, conversation and escalation services, notifications, retention and audit logging; acts as technical lead for architecture choices. | AI/ML (answer service); DevOps (environments, secrets); UX/Frontend (API contracts). | API contracts agreed early; integration status each week; security-fix estimates.
Frontend Developer | 1 | 10 | Builds the customer chat, admin KB screens, agent console and manager dashboard from the approved designs. | UX (designs); Backend (APIs); AI/ML (answer payload format). | Design-to-build questions raised early; component progress visible on the board; accessibility issues reported promptly.
UI/UX Designer | 0.4 | 4 | Researches flows, produces wireframes, prototype and final designs; runs usability sessions with agents; supports design acceptance. | Product Manager (priorities); Support agents (testers); Frontend (handoff). | Access to agents in Weeks 1-4; fast design decisions; clear definition of MVP screens.
QA Engineer | 0.8 | 8 | Defines test strategy; builds golden question set and evaluation script; runs functional, security, performance and UAT testing; tracks defects and quality metrics. | AI/ML and Backend (testable builds); Product Manager (reference answers); Support (UAT participants). | Testable builds at sprint review; defect triage within 1 business day; agreed severity definitions.
DevOps Engineer | 0.4 | 4 | Builds environments and CI/CD, secrets and TLS, monitoring and alerts, performance tuning, release and rollback; supports hypercare. | Backend and AI/ML (deployment needs); Cloud and email accounts; Security & Privacy Officer. | Early notice of infrastructure needs; deployment calendar; monitoring dashboards visible to PM.
Total | 6.1 | 61