## Risk Register
Risk Register - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Score = Probability x Impact. Rating: 1-4 Low, 5-9 Medium, 10-14 High, 15-25 Critical. Residual = target score after mitigation. Status reflects the simulated end of Sprint 2 (30 Jan 2026) and matches 13_Project_Status_Report. Blue = scoring inputs.
Risk ID | Risk | Category | Probability (1-5) | Impact (1-5) | Score | Rating | Owner (role) | Mitigation (preventive) | Contingency (if it happens) | Trigger / early warning | Residual P | Residual I | Residual Score | Status (as at 30 Jan 2026, simulated)
R01 | AI hallucination: the assistant states something not supported by the knowledge base (for example a wrong billing rule). | AI / Quality | 4 | 5 | 20 | Critical | AI/ML Engineer | Answer only from retrieved passages with citations (AIR-01); similarity threshold with 'I don't know' fallback (US-14); golden + adversarial set evaluated every sprint with a go-live gate of >= 85% accuracy and <= 5% unsupported answers; weekly human sample review during pilot. | Raise the threshold so more questions escalate; switch to 'search results only' mode (no generated text) for affected categories; kill-switch disables AI answers and routes everything to agents. | Unsupported-answer rate above 5% in any evaluation run, or any customer-reported wrong answer on billing, legal or security topics. | 2 | 5 | 10 | Mitigating - guardrails built in Sprint 2; first formal evaluation run in Sprint 3
R02 | Incorrect or irrelevant answers because retrieval picks the wrong passages (ambiguous questions, poor chunking). | AI / Quality | 3 | 4 | 12 | High | AI/ML Engineer | Chunking and ranking tuned in Sprint 2-3; evaluation reports list failing questions by cause; clarifying-question fallback; retrieval settings versioned (AIR-08). | Restrict pilot to the 10 best-covered categories; add manual 'pinned' answers for top questions; increase escalation offers. | Accuracy below 85% for two consecutive evaluation runs, or more than 15% of failures traced to retrieval. | 2 | 4 | 8 | Mitigating - tuning planned in WBS 5.4
R03 | Poor knowledge-base content: duplicate, outdated or conflicting articles produce wrong answers. | Data / Content | 4 | 4 | 16 | Critical | Product Manager | Content audit and cleanup before indexing (WBS 6.3) with Support SMEs; named content owner per category; mandatory review date per article (FR-04); fallback topics report to find gaps. | Publish only audited articles at pilot; unpublish disputed articles; extend cleanup into Sprint 3 with an extra SME day per week. | More than 10% of audited articles flagged outdated or conflicting, or golden-set failures traced to content exceed 15%. | 2 | 4 | 8 | Occurred (partly) - audit found 41 duplicates and 52 outdated articles; 17 still open (Issue I-02)
R04 | Data privacy: personal data is sent to the LLM provider, retained too long, or cannot be deleted on request. | Security / Privacy | 3 | 5 | 15 | Critical | Backend Developer | PII redaction before every LLM call (US-25); written provider terms with no training and minimal retention (AIR-06); 90-day retention and deletion tooling (US-26); data-minimising event design (US-23). | Suspend LLM calls and run in search-only mode; invoke incident process with the Security & Privacy Officer; notify affected customers if required by policy. | Provider terms still unconfirmed by end of Sprint 2 (6 Feb); redaction test below 100% on the seeded set; any real personal data found in logs. | 1 | 5 | 5 | Open - provider terms awaiting Legal confirmation (Dependency D-01)
R05 | Security vulnerabilities: broken access control, injection or prompt injection exposing data or tampering with answers. | Security / Privacy | 3 | 5 | 15 | Critical | Backend Developer | RBAC (US-05); rate limiting and validation (US-07); at least 20 prompt-injection cases; dependency scan in CI; dedicated security testing in Week 8 (WBS 9.3); Security & Privacy Officer review before Go/No-Go. | Hold go-live until Critical/High findings are fixed; temporarily disable affected feature; targeted retest. | Any Critical/High finding from scans or testing; failed access-control test. | 2 | 4 | 8 | Open - hardening planned for Sprint 4
R06 | LLM API dependency: provider outage, rate limits, latency spikes or model changes. | External / Technical | 3 | 4 | 12 | High | AI/ML Engineer | Provider abstraction layer (TR-04); pinned model version; timeouts, retries and graceful fallback message; secondary model validated in the Sprint 1 spike; rate-limit behaviour tested (US-27). | Switch to the fallback model/provider; run in search-only mode with escalation. | LLM error rate above 2% or p95 latency above 8 seconds for one hour. | 2 | 3 | 6 | Monitoring - fallback model validated in spike
R07 | LLM cost overrun beyond the 1,500 USD API budget. | Financial | 3 | 3 | 9 | Medium | Project Manager | Per-conversation token cap (US-13); caching of repeated questions; cost metrics and alerts at 70% and 90% (US-29); weekly spend check at status review. | Throttle usage, reduce retrieved passages, or use a smaller model; sponsor decides whether to extend budget. | More than 70% of the LLM budget spent before Week 9, or projected pilot cost above budget. | 2 | 2 | 4 | Monitoring - spend to 30 Jan well under plan
R08 | Scope creep: new feature requests (languages, integrations, extra channels) after the baseline. | Scope | 4 | 4 | 16 | Critical | Project Manager | Baselined scope with explicit Won't-Have list; MoSCoW; change-control process with impact assessment; Product Owner owns the backlog; changes only at sprint boundaries. | Apply the de-scope order (Scope doc, section 6) to make room; move requests to post-MVP backlog. | More than 2 unplanned stories requested per sprint; any request to change Must-Have scope after M2. | 2 | 3 | 6 | Mitigating - CR-001 (Spanish) assessed and deferred
R09 | Development delays from under-estimation by a new team with no historical velocity. | Schedule | 4 | 3 | 12 | High | Project Manager | Conservative planning (Sprint 1 at 28 points); velocity tracked each sprint; weekly burn-up; early integration in Sprint 3; Sprint 5 contains Should-Have items that can be dropped. | Apply the de-scope order; ask Sponsor for temporary extra capacity; re-plan Sprint 5 content. | Sprint velocity below 85% of plan, or any milestone forecast to slip by more than 2 working days. | 3 | 2 | 6 | Mitigating - Sprint 1 delivered 25 of 28 points; Sprint 2 delivered 34 of 36
R10 | Integration issues between UI, API, RAG service, database and email provider; end-to-end escalation flow breaks. | Technical | 3 | 4 | 12 | High | Backend Developer | Contract-first API (TR-05); staging from Week 1; integration tests in CI; dedicated integration work packages 8.1-8.3; weekly integrated demo from Sprint 3. | Short integration swarm of Backend, Frontend and QA; simplify flow (email-based reply) if in-app reply fails. | Integration tests red for more than 2 working days; 8.x task running late. | 2 | 3 | 6 | Open - integration work starts Sprint 3
R11 | Performance issues: slow answers or failures under concurrent load. | Technical | 3 | 3 | 9 | Medium | DevOps Engineer | Early smoke test in Sprint 4; caching; limit retrieved passages; load test of 50 sessions (US-27); scale resources. | Scale up instances; reduce context size; stream partial answers. | p95 above 8 seconds at 25 concurrent sessions during the Sprint 4 smoke test. | 2 | 2 | 4 | Open
R12 | Resource constraints and key-person dependency (single AI/ML Engineer; part-time UX, QA and DevOps). | Resource | 3 | 4 | 12 | High | Project Manager | Capacity plan by role; pair Backend and AI/ML on the RAG service; written handover notes; UX front-loaded to Weeks 1-4; backup named for each role. | Request a backup from the engineering pool via the Sponsor; descope Should-Have items. | Any key role unavailable for more than 3 working days, or planned capacity below 80%. | 2 | 3 | 6 | Monitoring
R13 | Delayed stakeholder decisions and limited availability of Support staff for usability tests and UAT. | Stakeholder | 3 | 3 | 9 | Medium | Project Manager | Decision log with a 2-business-day response expectation; UAT dates booked in Sprint 3; named UAT participants and backups; escalation to Sponsor. | Escalate to the Sponsor; run shorter UAT sessions with fewer participants and extend into Go/No-Go day. | A decision pending for more than 2 business days; UAT participants not confirmed by 13 Feb. | 2 | 2 | 4 | Mitigating - UAT nominations requested (Decision D3)
R14 | Agents resist or distrust the platform (fear of replacement, extra workload from poor escalations). | Organisational | 3 | 3 | 9 | Medium | Product Manager | Position the AI as handling routine questions so agents focus on complex work; involve agents in usability tests; full transcripts on escalation; training session; feedback channel. | Extend hypercare; adjust escalation categories and routing rules based on agent feedback. | Negative agent feedback in usability tests or UAT; agents bypass the queue. | 2 | 2 | 4 | Monitoring - usability sessions positive
R15 | Unrealistic accuracy expectations: stakeholders expect the AI to be right 100% of the time. | Requirements | 3 | 3 | 9 | Medium | Product Manager | Agree measurable targets (AIR-02, AIR-03); show evaluation results at every sprint review; make escalation a designed feature, not a failure. | Re-baseline targets through change control; agree category-specific scope. | Feedback at a review demanding zero-error behaviour or rejecting the fallback concept. | 2 | 2 | 4 | Mitigating - targets shown at Sprint 2 review
R16 | OTP emails not delivered or delayed, blocking customer sign-in. | External / Technical | 2 | 3 | 6 | Medium | Backend Developer | SPF/DKIM configured (TR-06); delivery monitoring; resend with rate limit; test sends in staging. | Switch to the backup email provider; temporary support-assisted sign-in. | OTP delivery success below 98% or median delivery above 60 seconds. | 1 | 3 | 3 | Open - domain verification pending (Dependency D-04)
R17 | Post-launch knowledge-base drift: content is not maintained and answer quality decays. | Operational | 3 | 3 | 9 | Medium | Product Manager | Content owner per category; review-date field and monthly review; fallback-topics report in dashboard; handover to Support Operations at closure. | Assign interim content owner; run a focused content sprint on top fallback topics. | Fallback rate rising for 3 consecutive weeks, or more than 10% of articles past review date. | 2 | 2 | 4 | Open - post-launch risk

## Heat Map
Risk Heat Map (live counts of risks per Probability x Impact cell)
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Counts are formulas on the register. Cell colour shows the rating band of the cell.
Probability \ Impact | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Severe
5 Almost certain | 0 | 0 | 0 | 0 | 0
4 Likely | 0 | 0 | 1 | 2 | 1
3 Possible | 0 | 0 | 6 | 4 | 2
2 Unlikely | 0 | 0 | 1 | 0 | 0
1 Rare | 0 | 0 | 0 | 0 | 0
Rating | Risks (current) | Risks (residual target)
Critical | 5 | 0
High | 5 | 1
Medium | 7 | 9
Low | 0 | 7
Total | 17 | 17

## Scoring Guide
Scoring Guide
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Scales used for this register (project-specific, set by the PM and agreed with the Product Manager).
Score | Probability | Impact (schedule / cost / quality / reputation)
1 | Rare: below 10% | Negligible: under 1 day delay; under 200 USD; no customer effect.
2 | Unlikely: 10-30% | Minor: 1-2 days delay; 200-500 USD; internal rework of part of a story.
3 | Possible: 30-50% | Moderate: 3-5 days delay; 500-1,500 USD; one story re-done; small number of customers affected.
4 | Likely: 50-75% | Major: 1-2 weeks delay or a milestone missed; over 1,500 USD; customer-visible wrong answers.
5 | Almost certain: over 75% | Severe: go-live blocked; personal-data breach; serious reputational harm.