## Sprint Overview
Sprint Plan - AI Customer Support Platform (5 sprints x 2 weeks)
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
This is a self-directed simulated PM project, and Scrum is being used as the proposed delivery methodology. No claim is made that this plan was executed in a real company. Planned stories and points are formulas on the 'Sprint Backlog' sheet. The full Product Backlog is in 04_Product_Backlog.xlsx.
Sprint | Start | End | Working days | Theme | Sprint goal | Features | Planned stories | Planned story points | Key dependencies | Expected deliverables | Review / demo
Sprint 1 | 2026-01-05 | 2026-01-16 | 10 | Foundation & Discovery | Establish the delivery foundation: approved charter and requirements baseline, environments with CI/CD, core data model, staff authentication with roles, a UX prototype and an evidence-based LLM/retrieval recommendation. | F01 Platform foundation; F02 Authentication (staff + roles); F05 UX prototype; F04 LLM/retrieval spike | 6 | 28 | Sponsor approval of charter; cloud account and budget released; LLM provider sandbox access; Support SMEs available for interviews | Approved Charter (M1); requirements baseline (M2); dev/staging environments + CI/CD; schema v1; staff login with RBAC; clickable prototype; LLM/embedding recommendation memo | 2026-01-16
Sprint 2 | 2026-01-19 | 2026-01-30 | 10 | Knowledge Base & AI Core | Make the knowledge base usable by the AI: admins can manage and bulk-import articles, published content is indexed, and the RAG service returns cited answers or a safe fallback, measured against a 100-question golden set. | F03 Knowledge Base Management; F04 AI Assistant (ingestion, RAG answers, guardrails, golden set) | 6 | 36 | Sprint 1 schema and RBAC; spike recommendation approved; cleaned KB export from Support (WBS 6.3); provider API keys | Admin KB screens (create/edit/publish/import); ingestion pipeline and vector index; RAG answer API with citations and fallback; golden set + evaluation script; KB audit report; Sprint 2 demo (M3) | 2026-01-30
Sprint 3 | 2026-02-02 | 2026-02-13 | 10 | Customer Chat Experience | Deliver the customer experience: customers sign in, chat with the assistant, see sources and history, and can request a human - with personal data redacted before any LLM call. | F05 Customer Chat; F06 Answer Feedback; F07 Conversation History; F08 Escalation request; F04 PII redaction; F02 Customer OTP sign-in | 6 | 34 | Sprint 2 RAG API and guardrails; design handoff (WBS 3.3); email provider domain verified; provider data-handling terms confirmed | Working customer chat with sources and AI label; email-OTP sign-in; feedback control; conversation history; 'Talk to a person' request; PII redaction; AI evaluation run #1; Sprint 3 demo (M4) | 2026-02-13
Sprint 4 | 2026-02-16 | 2026-02-27 | 10 | Human Handover, Analytics & Hardening | Close the loop with humans and measurement: agents work escalations end-to-end, customers receive replies, managers see analytics and security hardening is complete - feature complete at M5. | F08 Agent Console and reply notifications; F09 Analytics; F10 Security hardening | 6 | 34 | Sprint 3 escalation records; email provider for notifications; Support Manager feedback on agent workflow; UAT participants nominated | Escalation queue + agent console; customer reply (in-chat and email); event tracking + manager dashboard; security hardening; feature-complete build (M5); UAT plan ready | 2026-02-27
Sprint 5 | 2026-03-02 | 2026-03-13 | 10 | Readiness, Release & Closure | Prove readiness and release: privacy retention/deletion, audit logging, performance test, UAT sign-off, production pilot release, hypercare and project closure. | F10 Privacy retention and deletion; F11 Audit logging; F12 Release readiness (performance, UAT, deployment); F13 Guides and training | 6 | 29 | UAT participants; Go/No-Go attendance (Sponsor, Security & Privacy Officer); production environment and monitoring ready | UAT sign-off (M6); performance test report; runbook; admin/agent guides + training; Go/No-Go (M7); pilot release (M8); closure report (M9) | 2026-03-13
Total |  |  | 50 |  |  |  | 30 | 161
Formulas:
Working days = NETWORKDAYS([Start],[End])

## Sprint Backlog
Sprint Backlog (planned commitment per sprint)
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
One row per planned story, grouped by sprint. Detailed stories and acceptance criteria: 05_User_Stories.xlsx.
Sprint | Story ID | Deliverable | Epic | Priority | Story points | Primary role | Depends on | Persona
1 | US-01 | Environments + CI/CD pipeline | EP-1 Platform Foundation & DevOps | Must | 5 | DevOps Engineer | None | Developer
1 | US-02 | Schema v1 + migrations | EP-1 Platform Foundation & DevOps | Must | 5 | Backend Developer | None | Developer
1 | US-03 | Clickable prototype | EP-1 Platform Foundation & DevOps | Must | 5 | UI/UX Designer | None | Product Owner
1 | US-04 | Staff login | EP-2 Identity, Access & Security | Must | 5 | Backend Developer | US-02 | Support Agent, Manager or Admin
1 | US-05 | RBAC permission model | EP-2 Identity, Access & Security | Must | 3 | Backend Developer | US-04 | Admin
1 | US-11 | Spike report + recommendation | EP-4 AI Assistant (RAG) | Must | 5 | AI/ML Engineer | None | Product Owner
2 | US-09 | Admin KB editor | EP-3 Knowledge Base Management | Must | 5 | Frontend Developer | US-02, US-05 | Admin
2 | US-10 | Bulk import | EP-3 Knowledge Base Management | Should | 5 | Backend Developer | US-09 | Admin
2 | US-12 | Ingestion pipeline + vector index | EP-4 AI Assistant (RAG) | Must | 8 | AI/ML Engineer | US-02, US-11 | Admin
2 | US-13 | RAG answer API | EP-4 AI Assistant (RAG) | Must | 8 | AI/ML Engineer | US-12 | Customer
2 | US-14 | Guardrails + fallback | EP-4 AI Assistant (RAG) | Must | 5 | AI/ML Engineer | US-13 | Customer
2 | US-15 | Golden set + evaluation script | EP-4 AI Assistant (RAG) | Must | 5 | QA Engineer | US-09 | Product Owner
3 | US-06 | Customer email-OTP sign-in | EP-2 Identity, Access & Security | Must | 5 | Backend Developer | US-02 | Customer
3 | US-16 | Customer chat UI | EP-5 Customer Chat Experience | Must | 8 | Frontend Developer | US-03, US-06, US-13 | Customer
3 | US-17 | Answer feedback | EP-5 Customer Chat Experience | Should | 3 | Frontend Developer | US-16 | Customer
3 | US-18 | Conversation history | EP-5 Customer Chat Experience | Must | 5 | Backend Developer | US-02, US-16 | Customer
3 | US-19 | Escalation request flow | EP-6 Escalation & Agent Console | Must | 8 | Backend Developer | US-14, US-16 | Customer
3 | US-25 | PII redaction layer | EP-8 Privacy & Data Protection | Must | 5 | AI/ML Engineer | US-13 | Security & Privacy Officer
4 | US-07 | Security hardening | EP-2 Identity, Access & Security | Must | 5 | Backend Developer | US-04, US-05 | Security & Privacy Officer
4 | US-20 | Escalation queue | EP-6 Escalation & Agent Console | Must | 5 | Backend Developer | US-19, US-05 | Support Agent
4 | US-21 | Agent console | EP-6 Escalation & Agent Console | Must | 8 | Frontend Developer | US-20 | Support Agent
4 | US-22 | Reply notifications | EP-6 Escalation & Agent Console | Must | 5 | Backend Developer | US-21 | Customer
4 | US-23 | Event tracking | EP-7 Analytics & Reporting | Must | 3 | Backend Developer | US-16, US-19 | Support Manager
4 | US-24 | Manager dashboard | EP-7 Analytics & Reporting | Must | 8 | Frontend Developer | US-23 | Support Manager
5 | US-08 | Audit log | EP-2 Identity, Access & Security | Should | 3 | Backend Developer | US-05 | Support Manager
5 | US-26 | Retention + deletion | EP-8 Privacy & Data Protection | Must | 5 | Backend Developer | US-18, US-05 | Security & Privacy Officer
5 | US-27 | Performance test report | EP-9 Release Readiness | Must | 5 | QA Engineer | US-22, US-24 | Product Owner
5 | US-28 | UAT sign-off | EP-9 Release Readiness | Must | 8 | QA Engineer | US-07, US-16, US-21, US-22, US-24, US-25 | Support Manager
5 | US-29 | Production release + monitoring | EP-9 Release Readiness | Must | 5 | DevOps Engineer | US-01, US-27 | Executive Sponsor
5 | US-30 | Guides + training | EP-9 Release Readiness | Should | 3 | Product Manager | US-09, US-21 | Support Agent or Admin

## Capacity & Velocity
Capacity, Velocity and De-scope Plan
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
The team is new and has no historical velocity, so Sprint 1 is deliberately lighter. Planning velocity for later sprints is an assumption (about 34 points, +/- 10%) to be replaced by actual velocity after Sprint 2.
Sprint | Planned SP | Cumulative planned SP | % of MVP scope | Planning basis
1 | 28 | 28 | 17.39% | Ramp-up sprint: charter, requirements and environments take team time; 28 points planned.
2 | 36 | 64 | 39.75% | Peak AI build; 36 points is the highest commitment and sits at the top of the +/-10% band.
3 | 34 | 98 | 60.87% | 34 points: customer chat and escalation request with integration risk (R10).
4 | 34 | 132 | 81.99% | 34 points: agent console, analytics and hardening; feature complete at M5.
5 | 29 | 161 | 100% | 29 points: includes UAT, performance test and release; Should-Have items form the de-scope buffer.
Total | 161
De-scope order (applied only with Product Owner approval; Sponsor informed)
Order | Story | Points released | Priority | Action
1 | US-08 | 3 | Should | Defer audit logging to the post-MVP backlog (Should Have; basic access logs remain).
2 | US-30 | 3 | Should | Reduce guides to a one-page quick reference plus a 30-minute walkthrough.
3 | US-17 | 3 | Should | Keep thumbs up/down but drop the free-text comment.
4 | US-10 | 5 | Should | Drop the bulk-import screen; admins use the seed-load script and single-article editor.
5 | Escalate | - | - | If more is needed, Sponsor decides between (a) a smaller pilot (top 10 content categories) or (b) moving Go/No-Go; Must-Have stories are never silently cut.

## Definition of Done & Ready
Definition of Done (DoD) and Definition of Ready (DoR)
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Agreed at Sprint 1 planning and inspected at every retrospective.
# | Definition of Done: a story is Done when...
1 | Code is peer-reviewed through a pull request and merged to the main branch.
2 | Unit tests are written and passing; the CI pipeline is green.
3 | Acceptance criteria are verified by QA (or demonstrated) and accepted by the Product Owner.
4 | No Critical or High defects remain open on the story; Medium defects are triaged with a decision.
5 | The increment is deployed to staging and demonstrated at the sprint review.
6 | AI stories: evaluated against the golden set, result recorded, and no drop of more than 2 percentage points versus the previous run.
7 | Security basics: dependency scan has no Critical/High findings, no secrets in code, no personal data in logs.
8 | Logging and error handling exist for new endpoints.
9 | API documentation (OpenAPI) and user-facing text are updated.
10 | New customer-facing screens pass a keyboard-navigation and colour-contrast check.
# | Definition of Ready: a story may enter a sprint when...
1 | Written as 'As a [user], I want [feature], so that [benefit]'.
2 | Acceptance criteria are testable (Given / When / Then).
3 | Estimated at 8 points or fewer; larger stories are split first.
4 | Dependencies are identified and either complete or scheduled earlier.
5 | Designs exist for stories with a user interface.
6 | Priority set by the Product Owner and test data identified.

## Ceremonies
Scrum Cadence
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Sprint length 2 weeks, Monday to Friday. The PM facilitates ceremonies and owns impediment removal; the Product Manager owns the backlog.
Ceremony | When | Duration | Participants | Purpose / output
Sprint planning | Day 1 of sprint (Monday 10:00) | 2 hours | PM, Product Manager, delivery team, QA, UX | Sprint goal and committed stories; capacity and risks checked
Daily stand-up | Daily 09:30 | 15 minutes | Delivery team, PM | Progress and blockers; PM logs impediments and follows up the same day
Backlog refinement | Wednesday of week 2 | 1 hour | Product Manager, PM, technical leads | Next sprint's stories made 'Ready' (see Definition of Ready)
Weekly risk and status check | Thursday 11:00 | 30 minutes | PM and risk owners | Risk, issue and dependency logs updated; status report drafted
Sprint review / steering | Last Friday of sprint, 14:00 | 1 hour | Team, Sponsor, Support Manager, Product Manager, other stakeholders | Demo of working software; evaluation results; decisions logged
Retrospective | Last Friday of sprint, 15:30 | 1 hour | Delivery team and PM | Two or three improvement actions with owners