## Issue Log
Issue Log - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
Simulated log as at 30 Jan 2026 (end of Sprint 2); consistent with 13_Project_Status_Report. An issue is something that has already happened; risks that might happen are in 11_Risk_Register.
Issue ID | Issue | Raised | Raised by | Category | Severity | Owner | Action / resolution | Due | Status | Linked risk
I-01 | RBAC story (US-05) not finished in Sprint 1: permission-matrix questions took two extra days to settle. | 2026-01-16 | Backend Developer | Requirements clarity | Medium | Backend Developer | Permission matrix agreed with Product Manager and Security & Privacy Officer; story completed in Sprint 2. | 2026-01-20 | Resolved | R09
I-02 | 17 of the 52 outdated KB articles are still not updated after the audit (Support SMEs short of time). | 2026-01-28 | Product Manager | Content | High | Product Manager | Articles kept unpublished; Support Manager agreed 2 extra SME hours per day until 6 Feb; list tracked in the board. | 2026-02-06 | Open | R03
I-03 | Golden set: 72 of 100 questions have validated reference answers; US-15 carried into Sprint 3. | 2026-01-30 | QA Engineer | Quality | Medium | QA Engineer | Remaining 28 reference answers booked with Support SMEs; evaluation run #1 starts 9 Feb regardless, using validated items. | 2026-02-04 | Open | R01
I-04 | Flaky integration test blocked the CI pipeline on 14 Jan. | 2026-01-14 | DevOps Engineer | Technical | Low | DevOps Engineer | Test isolated and fixed; flaky-test quarantine rule added to the Definition of Done. | 2026-01-15 | Resolved | R10
I-05 | Staging environment answered the first request slowly (cold start) while preparing the Sprint 2 demo. | 2026-01-29 | QA Engineer | Technical | Low | DevOps Engineer | Keep-warm setting applied and verified before the demo; load test will confirm in Sprint 5. | 2026-01-29 | Resolved | R11
Open issues | 2