## Dependency Log
Dependency Log - AI Customer Support Platform
SIMULATED PROJECT - Self-directed portfolio case study. Not professional experience, not client work, not employment. All people, figures and outcomes are fictional.
External and cross-team dependencies tracked by the PM. Status is the simulated position at 30 Jan 2026. Task-to-task schedule dependencies are in 07_Project_Timeline and 08_Gantt_Chart.
Dep. ID | Dependency | Type | Needed for (WBS / story / requirement) | Provider / owner | Needed by | Raised | Status (30 Jan 2026) | RAG | Notes
D-01 | Provider data-handling terms (no training on our data, minimal retention) confirmed by Legal and Security | External / Governance | AIR-06, US-25, 5.4 | Hannah Weber (Security & Privacy Officer) | 2026-02-06 | 2026-01-23 | Open | Amber | Blocks sending real customer data to the LLM; test data only until confirmed. Linked risk R04.
D-02 | LLM API keys and quota for build and evaluation | External | 5.2, 5.3 | AI/ML Engineer with provider | 2026-02-02 | 2026-01-12 | Complete (28 Jan) | Green | Quota sufficient for evaluation runs; spend tracked weekly (R07).
D-03 | Cleaned KB export from Support (approx. 280 articles) | Internal | 6.2, 5.2 | Aiden Park (Knowledge & Content Lead) | 2026-01-23 | 2026-01-12 | Delivered with exceptions | Amber | Delivered on time; 17 flagged articles still being rewritten (Issue I-02).
D-04 | Email sending-domain verification (SPF/DKIM) for OTP and notification emails | External | 8.1, 4.3, US-06 | DevOps Engineer with IT (DNS owner) | 2026-02-02 | 2026-01-26 | In progress | Amber | DNS change requested 28 Jan. Linked risk R16.
D-05 | Five support agents available for usability sessions | Internal | 3.3 | Sofia Lindqvist (Support Manager) | 2026-01-22 | 2026-01-12 | Complete (20-22 Jan) | Green | Sessions held; findings fed into design handoff.
D-06 | UAT participants nominated (at least 3 agents plus backup) | Internal | 9.5, 9.6, US-28 | Sofia Lindqvist (Support Manager) | 2026-02-13 | 2026-01-30 | Open | Green | Requested 30 Jan; dates 2-6 Mar. Linked risk R13.
D-07 | Cloud account and non-labour budget released | Internal | 10.1 | Finance Partner | 2026-01-08 | 2026-01-05 | Complete (8 Jan) | Green | -
D-08 | Design handoff before chat UI build | Internal (technical) | 3.3 to 7.2 | UI/UX Designer | 2026-01-23 | 2026-01-19 | Complete (23 Jan) | Green | Handoff package accepted by Frontend Developer.
D-09 | Reference answers validated by Support SMEs for the golden set | Internal | 9.1, US-15 | Elena Rossi (Product Manager) | 2026-01-30 | 2026-01-19 | Late (72 of 100) | Amber | See Issue I-03; evaluation run #1 uses validated items.
D-10 | Security & Privacy Officer review slot before Go/No-Go | Internal | 9.3, 10.3 | Hannah Weber (Security & Privacy Officer) | 2026-03-03 | 2026-01-30 | Planned | Green | Provisionally booked 27 Feb to 3 Mar.
D-11 | Sponsor and Security & Privacy Officer attend Go/No-Go on 9 Mar | Internal | 10.3 | Marcus Hale (Executive Sponsor) | 2026-03-09 | 2026-01-30 | Planned | Green | Calendar hold sent.
D-12 | Stable RAG answer API before chat and escalation APIs are built | Internal (technical) | 5.3 to 4.4 | AI/ML Engineer | 2026-02-02 | 2026-01-19 | Complete (30 Jan) | Green | Demonstrated at the Sprint 2 review (M3).
Amber / Red | 4 amber, 0 red of 12 dependencies